## Requirements-Tracker
#No. | Requirements | Sprint-01 |  | Sprint-02 |  | Sprint-03 |  | Sprint-04 |  | Sprint-05 |  | Sprint-06 |  | Work items | Status | Commets
1 | Material UI | Start Date | End date | Start Date | End date | Start Date | End date | Start Date | End date | Start Date | End date | Start Date | End date | Flutter | Inprogress
2 | Floating Buttons | [12 empty] | php
3 | Buttons ( Image / system ) | [12 empty] | API | Done
4 | Slider buttons | [13 empty] | Done
5 | Search box | [13 empty] | ToDo
6 | Drop down | [13 empty] | ToDo
7 | Text Box
8 | Virtual Number Pad
9 | Grids
10 | panded items
11 | Lists | [13 empty] | ToDo
12 | Carousal vertical / horizontal with left and right | [13 empty] | Inprogress
13 | DatePicker (MM / dd / yyyy)
14 | Tabs
15 | Navigation Bar
16 | Dialogs ( alert/ warning)
17 | PDF Viewer
18 | Icons and logos
19 | Images
20 | Menu bar
21 | Cards
22 | Theme and colors
23 | Stacks and containers
24 | Animations ( hero )
25 | Loading UI
26 | Fonts and types
27 | Labels and tags
28 | Hex Color Converter.
29 | Multiple Image Picker with Add and Remove image
30 | DataTable Utility
31 | LazyLoading or Infinite Loading
32 | Barcode UI
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Note on I1: New User: 18th March - 27th March(2025)

## Sheet3
1. Material UI | Material UI | Material UI
2. Floating Buttons | Floating Buttons | Floating Buttons
3. Buttons ( Image / system ) | Buttons ( Image / system ) | Buttons ( Image / system )
4. Slider buttons | Slider buttons | Slider buttons
5. Search box | Search box | Search box
6. Drop down | Drop down | Drop down
7. Text Box | Text Box | Text Box
8. Virtual Number Pad | Virtual Number Pad | Virtual Number Pad
9. Grids | Grids | Grids
10. Expanded items | panded items | panded items
11. Lists | Lists | Lists
12. Carousal vertical / horizontal with left and right | Carousal vertical / horizontal with left and right | Carousal vertical / horizontal with left and right
13. DatePicker (MM / dd / yyyy) | DatePicker (MM / dd / yyyy) | DatePicker (MM / dd / yyyy)
14. Tabs | Tabs | Tabs
15. Navigation Bar | Navigation Bar | Navigation Bar
16. Dialogs ( alert/ warning) | Dialogs ( alert/ warning) | Dialogs ( alert/ warning)
17. PDF Viewer | PDF Viewer | PDF Viewer
18. Icons and logos | Icons and logos | Icons and logos
19. Images | Images | Images
20. Menu bar | Menu bar | Menu bar
21. Cards | Cards | Cards
22. Theme and colors | Theme and colors | Theme and colors
23. Stacks and containers | Stacks and containers | Stacks and containers
24. Animations ( hero ) | Animations ( hero ) | Animations ( hero )
25. Loading UI | Loading UI | Loading UI
26. Fonts and types | Fonts and types | Fonts and types
27. Labels and tags | Labels and tags | Labels and tags
28. Hex Color Converter. | Hex Color Converter. | Hex Color Converter.
29. Multiple Image Picker with Add and Remove image | Multiple Image Picker with Add and Remove image | Multiple Image Picker with Add and Remove image
30. DataTable Utility | DataTable Utility | DataTable Utility
31. LazyLoading or Infinite Loading | LazyLoading or Infinite Loading | LazyLoading or Infinite Loading
32. Barcode UI | Barcode UI | Barcode UI

## Sprint03
Issue Type | Key | Summary | Status | Sprint | Assignee | Due date | Labels | Created | Updated | Reporter
Story | SCRUM-77 | Integrate User relation with Fastkeys, Orders, Fastkey item Grid | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-03-05 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-60 | Add Fast key Product Table | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-02-14 | 2025-03-13 | Ranjeet Chirutkar
Story | SCRUM-73 | Bloc, Model and Repositories | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-03-05 | 2025-03-13 | Ranjeet Chirutkar
Task | SCRUM-59 | Add Fast Key Table | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-02-14 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-58 | Add Orders Table to handle order details | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-02-14 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-51 | Select Product from Grid layout and update to Order layout | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-02-14 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-45 | Flutter app theme for dark / light mode | Done | Pinaka Sprint 3 | Shravan Bele |  |  | 2025-02-06 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-66 | Map Fastkey preferences with user setting | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-02-27 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-65 | Create a user preference table | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-02-27 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-76 | Add User table | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-03-05 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-72 | Network Helper class | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-03-05 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-18 | Plugin Settings and Configurations | Done | Pinaka Sprint 3 | Kumaraswamy D |  |  | 2025-01-16 | 2025-03-18 | Ranjeet Chirutkar
Subtask | SCRUM-25 | Theme and icons configuration | Done | Pinaka Sprint 3 | Kumaraswamy D |  |  | 2025-01-16 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-78 | Order history table layout | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-03-06 | 2025-03-13 | Ranjeet Chirutkar
Story | SCRUM-69 | CRUD endpoints | Done | Pinaka Sprint 3 | Kumaraswamy D |  |  | 2025-03-05 | 2025-03-18 | Ranjeet Chirutkar

## Sprint04
Issue Type | Key | Summary | Status | Sprint | Assignee | Due date | Labels | Created | Updated | Reporter
Epic | SCRUM-1 | Setup Framework | To Do |  |  |  |  | 2025-01-14 | 2025-01-14 | Ranjeet Chirutkar
Epic | SCRUM-2 | UI Development | To Do |  | Ranjeet Chirutkar |  |  | 2025-01-14 | 2025-01-31 | Ranjeet Chirutkar
Epic | SCRUM-3 | Service integration | In Progress |  |  |  |  | 2025-01-14 | 2025-01-14 | Ranjeet Chirutkar
Epic | SCRUM-4 | Peripherals Integration | To Do |  | Ranjeet Chirutkar |  |  | 2025-01-14 | 2025-01-31 | Ranjeet Chirutkar
Epic | SCRUM-14 | WordPress Plugin Development | To Do |  |  |  |  | 2025-01-16 | 2025-01-16 | Ranjeet Chirutkar
Epic | SCRUM-15 | WooCommerce Integration- Backend | To Do |  | Kumaraswamy D |  |  | 2025-01-16 | 2025-03-18 | Ranjeet Chirutkar
Epic | SCRUM-56 | SQLite Database implementation and integration with sync | To Do |  | Ranjeet Chirutkar |  |  | 2025-02-14 | 2025-02-14 | Ranjeet Chirutkar
Epic | SCRUM-67 | API Development | To Do |  |  |  |  | 2025-03-05 | 2025-03-05 | Ranjeet Chirutkar
Story | SCRUM-26 | Payment gateway setup (SDK + Backend) | To Do |  | Shravan Bele |  |  | 2025-01-23 | 2025-03-18 | Ranjeet Chirutkar
Subtask | SCRUM-27 | Flutter Payment SDK integration | To Do |  |  |  |  | 2025-01-30 | 2025-01-30 | Ranjeet Chirutkar
Subtask | SCRUM-28 | Backend Verification and logs | To Do |  |  |  |  | 2025-01-30 | 2025-01-30 | Ranjeet Chirutkar
Story | SCRUM-71 | Plugin settings API | To Do |  | Kumaraswamy D |  |  | 2025-03-05 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-74 | Auth API integration | To Do | Pinaka Sprint 4 | Ranjeet Chirutkar |  |  | 2025-03-05 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-70 | Woo Commerce integration REST API | To Do | Pinaka Sprint 4 | Kumaraswamy D |  |  | 2025-03-05 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-79 | Start / End shift | To Do | Pinaka Sprint 4 | Shravan Bele |  |  | 2025-03-11 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-80 | Product API | In Progress | Pinaka Sprint 4 | Kumaraswamy D |  |  | 2025-03-13 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-81 | Fast key API | To Do | Pinaka Sprint 4 | Kumaraswamy D |  |  | 2025-03-13 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-82 | Orders API | To Do | Pinaka Sprint 4 | Kumaraswamy D |  |  | 2025-03-13 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-83 | Categories API | To Do | Pinaka Sprint 4 | Kumaraswamy D |  |  | 2025-03-13 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-84 | Provide access to user roles in backend | To Do | Pinaka Sprint 4 | Kumaraswamy D |  |  | 2025-03-18 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-85 | Authentication API changes | In Progress | Pinaka Sprint 4 | Kumaraswamy D |  |  | 2025-03-18 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-87 | Product API integration | In Progress | Pinaka Sprint 4 | Ranjeet Chirutkar |  |  | 2025-03-18 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-88 | FastKey API Integration | To Do | Pinaka Sprint 4 | Ranjeet Chirutkar |  |  | 2025-03-18 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-89 | Order API Integration | To Do | Pinaka Sprint 4 | Ranjeet Chirutkar |  |  | 2025-03-18 | 2025-03-18 | Ranjeet Chirutkar
Epic | SCRUM-86 | App Settings and Misc Features | To Do |  |  |  |  | 2025-03-18 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-90 | Categories API Integration | To Do |  | Ranjeet Chirutkar |  |  | 2025-03-18 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-91 | Assets API integration | To Do |  | Ranjeet Chirutkar |  |  | 2025-03-18 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-92 | Create a popup dialog for the store id to capture at first time installation | In Progress | Pinaka Sprint 4 | Ranjeet Chirutkar |  |  | 2025-03-18 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-93 | Assets API | To Do |  |  |  |  | 2025-03-18 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-75 | Category screen changes | In Progress | Pinaka Sprint 4 | Shravan Bele |  |  | 2025-03-05 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-13 | UI Components | In Progress | Pinaka Sprint 4 | Ranjeet Chirutkar |  |  | 2025-01-16 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-77 | Integrate User relation with Fastkeys, Orders, Fastkey item Grid | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-03-05 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-60 | Add Fast key Product Table | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-02-14 | 2025-03-13 | Ranjeet Chirutkar
Story | SCRUM-73 | Bloc, Model and Repositories | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-03-05 | 2025-03-13 | Ranjeet Chirutkar
Task | SCRUM-59 | Add Fast Key Table | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-02-14 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-58 | Add Orders Table to handle order details | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-02-14 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-51 | Select Product from Grid layout and update to Order layout | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-02-14 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-45 | Flutter app theme for dark / light mode | Done | Pinaka Sprint 3 | Shravan Bele |  |  | 2025-02-06 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-66 | Map Fastkey preferences with user setting | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-02-27 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-65 | Create a user preference table | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-02-27 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-76 | Add User table | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-03-05 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-72 | Network Helper class | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-03-05 | 2025-03-18 | Ranjeet Chirutkar
Story | SCRUM-18 | Plugin Settings and Configurations | Done | Pinaka Sprint 3 | Kumaraswamy D |  |  | 2025-01-16 | 2025-03-18 | Ranjeet Chirutkar
Subtask | SCRUM-25 | Theme and icons configuration | Done | Pinaka Sprint 3 | Kumaraswamy D |  |  | 2025-01-16 | 2025-03-18 | Ranjeet Chirutkar
Task | SCRUM-78 | Order history table layout | Done | Pinaka Sprint 3 | Ranjeet Chirutkar |  |  | 2025-03-06 | 2025-03-13 | Ranjeet Chirutkar
Story | SCRUM-69 | CRUD endpoints | Done | Pinaka Sprint 3 | Kumaraswamy D |  |  | 2025-03-05 | 2025-03-18 | Ranjeet Chirutkar

## Check list
#.No | work Items | References
1 | POS demo | Pinaka POS Overview - https://youtu.be/vOrDHlcqduc Pinaka Shifts Overview - https://youtu.be/IMlDvULcz5g Pinaka Discounts Overview - https://youtu.be/XJ7nlNPoHHo Pinaka Coupons Overview - https://youtu.be/C7vPKIUcqSE
2 | Agile process
3 | Jira tool to setup

## Sprint 4 -goal
Sprint 04-Goal
Services integration should be started and target:
1. product searching
2. Fast key tab creation and saving
3. Orders creation

## Git
commands/links
Download Git from link-> | https://git-scm.com/downloads
get init
create text file from command prompt | touch names.txt
changes mades to git repository untracked files) | git status
git add .(or) git add names.txt (like added in above step)
shows the folder in green -meaning the file is in repository for everyone access | git status
| git commit -m "names.txt file added" | -m means message added.
to added content to file names.txt | vi names.txt | type - names like apple, mango, coke
to check the content in the text file | cat names.txt
| git restore --stagged names.txt | data added will be removed.
| git status | all data added will cleaned
| git log | complete history made
reset will remove the above code history of the typed event | git reset nfslfjdlflkfjdslfdlf
git branch feature
git checkout feature
git commit
git checkout main
git commit

## Sheet1
pheripheral integration |  |  |  |  | April end
| login | home page | payment Summary page |  | endto end flow
|  | Fast keys | ( 6 Api) |  |  | using peripherals
|  | categorits |  |  |  | user login
|  | Search |  |  |  | create order
[6 empty] | add the items to order | scan
| Raju | order panel |  |  |  |  | search
|  | payments |  |  |  |  | select (fast keys)
bar codes
Thermal printer
cash drawer
Pinaka Server (website)
ui- create user | means merchant
id
password
back end lo details will fetch | store name | back end lo details will fetch
2. create a web ste |  |  | create a flow for merchant on boarding
|  |  | prepare a check list for pre requirst | items required
check list to store
device setup

## April Milestones
kumar | 1 | merchant onboarding | rigister to pinaka and web site creation happen and creates users and shifs. |  |  |  | Sprin 5 Backlogs
|  |  | process/setup |  |  |  | main page |  |  | Payments
|  |  | prepare checklist for all pre-requisite |  |  |  | navigation panel | body panlel | order panel | summary page
|  |  | iedntity all dependicies | [5 empty] | pay | done /Print /
2
rajeet |  | devce - store setup
prepare checklist for all pre-requisite
|  |  | idetify dependencides (if any) |  |  | 1 | print peripherals
Scan
Sarole Team | 3 | endto end flow |  |  |  |  | order panel pay button
|  |  | using peripherals | scan
|  |  | user login | search |  | 2 | payments page
|  |  | create order | select (fast keys) |  |  | summary page
|  |  | add the items to order |  |  |  | done/print /
[6 empty] | 3 | merchant onboarding | with all API's | domain and sub domains
[6 empty] | 4 | device /store setup check list
Raju | landing page | fast keys/products | shrink the image with app. Changes | done |  | 5 | end to end flow
|  |  | new orders icon with limit orders | pending
order summary page wih discount details.
| Payment summary |  | changed the resolution to agreed pixel | 1440/1024 - 1920/1080
|  |  | changed the UI changes - payment mode | cash-Card-Wallet-EBT
|  | pop ups | Partial Payment Recived
|  |  | transaction successfully done | animation for tick mark | micro interactions -animation
|  |  | print, email,SMS | void button fill color.
Email/SMS -both

## GIT repo
Record this token somewhere secure, it can't be viewed or retrieved once you close this window. | ATCTT3xFfGN02qJz113PSpTautGlqodr6P-iuAWcr2fLwFbM1Rtn1DDAlMDVgUZAkq3fUV51Y59g0da8LIbL2OMil0Ir6HNLDQzM0OpXUJaTAPkyLg6KcSaVsb2W5XAWwku3xem-c8I9yl9p4SYcGILlykrLA_xvsTAKn7vTGIfYQUlIjYcX7KY=8902C727 | Password123$**
Provide this token in the Authorization header as a bearer token when making requests to Bitbucket APIs, for example: | Authorization: Bearer ATCTT3xFfGN02qJz113PSpTautGlqodr6P-iuAWcr2fLwFbM1Rtn1DDAlMDVgUZAkq3fUV51Y59g0da8LIbL2OMil0Ir6HNLDQzM0OpXUJaTAPkyLg6KcSaVsb2W5XAWwku3xem-c8I9yl9p4SYcGILlykrLA_xvsTAKn7vTGIfYQUlIjYcX7KY=8902C727
To clone this repository using this token, run | git clone https://x-token-auth:ATCTT3xFfGN02qJz113PSpTautGlqodr6P-iuAWcr2fLwFbM1Rtn1DDAlMDVgUZAkq3fUV51Y59g0da8LIbL2OMil0Ir6HNLDQzM0OpXUJaTAPkyLg6KcSaVsb2W5XAWwku3xem-c8I9yl9p4SYcGILlykrLA_xvsTAKn7vTGIfYQUlIjYcX7KY=8902C727@bitbucket.org/pinakapos/repoflutterpinakapos.git

## Sprint 5-add ons
#.N0 | EPIC | Story | Task | Relates to Story | Status | Sprint 5 |  | backlogs | Details | 75
1 | 67 |  | 81 | 116 | TO DO | 5 | kumar | Fastkey update API
|  |  |  | 117 | TO DO | 5 |  | Fastkey Delete API |  | adding a category at fast key level
|  |  |  | 118 | TO DO | 5 |  | Reorder prodct items in fastkey/category
|  |  |  | 119 | TO DO |  |  | Delete product item in fast key
2 | 67 | 85 |  | 84 | TO DO |  |  | Authenticate API | provide access to user role in backend
Change in request for Auth Pass store token to the authorise request Please add device id, client id, store id In response if subscription is not valid send an error If store id is not valid with device id, send and error send subscription end date in response Do we need role for the current user as response based on
3 | 67 |  | 80 |  |  |  | Shravan | Product API search by product item only ( sku or item name ) Result should be only product item not any category or other fields, also exclude variants from the search results Global and fast key item search should only target for product search | Add complete requirements into confluence and update in this ticket If required we can add new sub task and start working on those. Are we planning on product search API with variants ? No Keep it as a backlog for now. - @Shravan Bele
|  |  | 82 |  |  |  |  | Order API's cjjangesrpesed for next sprinnt -create, get, update, delete orders | Shravann
|  |  | 83 |  |  |  |  | get list of main categories. | kumar
get list of sub categories
get list of products/sub categores/varients.
70
[6 empty] | 75 | Raju | Shravan Bele please make a note of following Add fast key popup Add Fast key product popup Theme color changes +- buttons are small on variants popup | Raju
79
84
89

## Sheet2
1 | Screens
Login
Fast keys
search
Order Panel
2 | Introduction to Andriod Studio (IDE)
set up
link to repo
code update/build
gen Apk
Deploy/Test
3 | Introduction to Jira
Process
Significance
other tools like confluence
Bit Bucket
5 | Serole-Flutter App
code Review
update comments
codig standards