## Team_Deatils
To be updated

## Daily Tracker
| Project | PINAKA -POS
#No. | Task Name | Sub Task | Task Type | Environment | Assigned To | Description | Start Date | End Date | Comments | Status | % Completed
1 | Github | <mention any sub task if any > |  | Flutter | Swapna |  |  |  | Inprogress
2 | Github |  |  | php | Swapna
3 | Domain |  |  | API | Swapna |  |  |  | Done
4 | Rest A |  |  |  | Swapna |  |  |  | Done
5 | Figma |  |  |  | Raju |  |  |  | ToDo
6 | Codings |  |  |  | Swapna |  |  |  | ToDo
7 | Application |  |  |  | Swapna
8 | products | list of items (eg) | Design/content/UI |  | Raju
9 |  |  |  |  | Swapna
10
11 | [8 empty] | ToDo
12 | [8 empty] | Inprogress
13 |  |  |  | A
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Sheet1
Name | Task | Description | Duration | Status
Swapna | github | 1.learned the github basics. | 26-03-2025 to 02-04-2025 | completed
2.created the repository of flutter project using github.
3.created a branch from main and performed all operations of github in it.
4.Developed a basic login module using Flutter for the Pinaka POS project.
| Domain | 5.Reviewed the domain overview of the Pinaka POS project.
| pinaka pos project | 6.Cloned the Pinaka project from GitHub and conducted a thorough review of its project structure. | 03-04-2025 to 07-04-2025 | completed
| Api calls overview | 7.tested the api calls using postman tool. | 2025-04-08 | completed
| Flow of project | 8. Created the Class and Sequence Diagrams for the PiNaKa POS (Point of Sale) project. | 2025-04-09 | completed
Suneela | Project Discussion | 1.Attended the project discussion meeting and understand the new requriments. | 2025-04-01 | completed
| Android studio and source tree | 2.Install the android studio and source tree complete the set up | 2025-04-02 | completed
| git hub | 3.Install the git hub and clone the pinako code and run the code | 2025-04-03 | completed
| Understand the code | 4.Understand the code for API calls,screens,widgets and utilities | 2025-04-04 | completed
| Understand the code | 5.Understand the code for API calls,screens,widgets and utilities and attended the meeting | 2025-04-07 | completed
| install postman for testing api calls. | 6.install the postman site and clone the api code and test the api calls for check the status | 2025-04-08 | completed
| Flow of project | 7.Draw the class and sequence diagrams for main screen. | 2025-04-09 | completed
Madhuri | pinaka pos project | 1. Conducted a thorough review of its project structure of pinaka POS. | 07-04-2025 to 08-04-2025 | completed
| Flow of project | 2.Draw the class and sequence diagrams for main screen. | 2025-04-09 | completed
Revathi Priya | php | 1.learned the php basics. | 2025-04-08 | completed
| installation | 2.done with the installation of php. | 2025-04-09 | completed
Krishnamraju | Project Discussion | 1.Discussed about the project model. | 2025-03-24 | completed
| design preview | 2.Reviewed the previous figma design. | 25-03-2025 to 26-03-2025 | completed
| Re-designing | 3.Re-designed the login and fest key screens of pinaka POS. | 2025-03-27 | completed
| Re-designing | 4.Re-designed the categories and product summary screens of pinaka POS. | 2025-03-28 | completed
| Designing | 5.designed the billing screens of pinaka POS.and worked on alekya logo. | 31-03-2025 to 01-04-2025 | completed
| Designing | 6..designed the product variants pop-ups of pinaka POS. | 2025-04-02 | completed
| Designing | 7..designed the product cart section of pinaka POS. and converted entire screen into 1920 * 1080 size. | 03-04-2025 to 04-04-2025 | completed
| Designing | 8..designed the payment transaction and print receipt pop-ups of pinaka POS. | 2025-04-07 | completed
| Designing | 9.modified the new color and fonts for existing screens of pinaka POS. | 2025-04-08 | completed
| Project Discussion | 10.Discussed about the redesign project model and started working on it. | 2025-04-09 | in-progress